## Sheet1
Project--> | Advanced Fake News Detection System |  | TimeLine: 2-3 weeks |  |  | To connect the webpage to the model we chose flask as a web development framework, which is deployed on Amazon Web Services (AWS) instance. The input received from the website will be given to the AWS-EC2 instance. This instance has all required files of machine learning models, flask files, and the front-end web server. Once the required models are dumped from the machine learning model we will further use only those dumped models in the flask file.
| Selected Base paper: | https://drive.google.com/file/d/1LS-0QMCthAGMeHBbSoRCSmv9RAgcD3qv/view?usp=share_link
|  |  | Project Phase | Tasks | ETA(Tentative)
|  |  | Information Retrival | 1.Using web crawler data collection,datasets using Scrapy (https://scrapy.org/),Storing them has train and test data. | 12Hrs
WorkFlow: | https://drive.google.com/file/d/15Y6x21bUHx2OYYWn46z913g100hufMQJ/view?usp=share_link
|  |  | Data Preprocessing | 1.Stop Word Removal - are more common and hold less useful information.(Natural Language Toolkit – (NLTK) library to remove stop word) | 6Hrs
2.Punctuation Removal(tokenization)
3.Stemming(tokenization)
|  |  | NLP | Word Vector Representation-->for feature selection and Before using a machine learning system, text must be translated into numbers. | 12-18Hrs
1. TF-IDF Vectorizer.(TF-IDF uses word frequency to identify words that are more important (occur more frequently) in a document. The TF-IDF Vectorizer converts documents into tokens, learns vocabulary, inverses document frequency weightings, and allows you to cipher new documents.
2. Countvectorizer (The Count Vectorizer creates an encoded vector that comprises the full vocabulary’s length as well as the frequency with which each word appears in the document.)
|  |  | Model Building & Training | Algorithms-->(Train the model with train data)-- Aggregation of model outputs is considered | 24Hrs
1.Logistic Regression
2.Decision Tree
3.KNN
4.Random Forest
5.Gradient Boosting
|  |  | Predicting the Output | Based on Classification Metrics | 6Hrs
-Confusion matrix
-Accuracy
-Precision
-Recall
-F1 score
|  |  | Mitigate the Impact of Fake News | If Output is FAKE--> | 8-12Hrs
auto-populate the spreader's inbox with Official News using email bots or email filtering tools
Note:-(Still need to figure out, how to identify the original source of News)